## #1(a)
Activity | Completion Time |  | Start Time |  | Finish Time
A | 30 | AStartTime | 0 | AFinishTime | 30
B | 5 | BStartTime | 30 | BFinishTime | 35
C | 2 | CStartTime | 0 | CFinishTime | 2
D | 3 | DStartTime | 32 | DFinishTime | 35
E | 7 | EStartTime | 0 | EFinishTime | 7
F | 25 | FStartTime | 10 | FFinishTime | 35
G | 15 | GStartTime | 0 | GFinishTime | 15
H | 10 | HStartTime | 23 | HFinishTime | 33
I | 2 | IStartTime | 33 | IFinishTime | 35
J | 10 | JStartTime | 35 | JFinishTime | 45
K | 15 | KStartTime | 0 | KFinishTime | 15
L | 30 | LStartTime | 45 | LFinishTime | 75
|  |  |  | Finish Time | 75 | minutes
|  |  |  | a) | 75 minutes

## #1(b)
| Activity | Completion Time |  | Start Time |  | Finish Time
| A | 30 | AStartTime | 0 | AFinishTime | 30
| B | 5 | BStartTime | 33 | BFinishTime | 38
| C | 2 | CStartTime | 0 | CFinishTime | 2
| D | 3 | DStartTime | 35 | DFinishTime | 38
Add 6 mins | E | 13 | EStartTime | 0 | EFinishTime | 13
| F | 25 | FStartTime | 13 | FFinishTime | 38
| G | 15 | GStartTime | 0 | GFinishTime | 15
| H | 10 | HStartTime | 26 | HFinishTime | 36
| I | 2 | IStartTime | 36 | IFinishTime | 38
| J | 10 | JStartTime | 38 | JFinishTime | 48
| K | 15 | KStartTime | 0 | KFinishTime | 15
| L | 30 | LStartTime | 48 | LFinishTime | 78
[5 empty] | Finish Time | 78 | minutes
|  |  |  | b) | 78 - 75 = | 3 | minute delay

## #2
Crash Cost
[6 empty] | Crash | Cost | Crash | Max | per Week
Activity | Completion Time |  | Start Time |  | Finish Time | Time | Normal | Cost | Crash | Saved
A | 5 | AStartTime | 0 | AFinishTime | 3 | 3 | 20 | 30 | 2 | 5 | 2
B | 3 | BStartTime | 0 | BFinishTime | 2 | 2 | 10 | 20 | 1 | 10 | 1
C | 4 | CStartTime | 3 | CFinishTime | 7 | 2 | 16 | 24 | 2 | 4 | 0
D | 6 | DStartTime | 3 | DFinishTime | 9 | 3 | 25 | 43 | 3 | 6 | 0
E | 5 | EStartTime | 2 | EFinishTime | 7 | 4 | 22 | 30 | 1 | 8 | 0
F | 7 | FStartTime | 2 | FFinishTime | 9 | 4 | 30 | 48 | 3 | 6 | 0
G | 9 | GStartTime | 7 | GFinishTime | 15 | 5 | 25 | 45 | 4 | 5 | 1
H | 8 | HStartTime | 9 | HFinishTime | 15 | 6 | 30 | 44 | 2 | 7 | 2
[7 empty] | 178 |  |  | 39
|  |  |  | Finish Time | 15
[7 empty] | Total Price: | 217 | million dollars
| a) | 217 million dollars
| b) | Crashing Activity B for 1 week nets a 2 week push. (1 week shift of F and H)(D now takes the same time as F) (1 week push for E and G)(E now takes the same time as C)
| c) | The time it takes to do Activity C only affects G. Also now that Activity B is crashed C and E finish at the same time. Even if C finishes sooner you will still have to wait for E to finish to start G.

## #3
From | To | On Route | Distance | Nodes | Net Flow |  | Supply/Demand
Seattle | Portland | 0 | 3 | Seattle | 1 | = | 1
Seattle | Boise | 0 | 9 | Portland | 0 | = | 0
Seattle | Butte | 1 | 10 | Bosie | 0 | = | 0
Portland | Seattle | 0 | 3 | Butte | 0 | = | 0
Portland | Boise | 0 | 7 | Salt Lake City | 0 | = | 0
Boise | Portland | 0 | 7 | Billings | 0 | = | 0
Boise | Seattle | 0 | 9 | Grand Junction | 0 | = | 0
Boise | Butte | 0 | 7 | Cheyenne | 0 | = | 0
Boise | Cheyenne | 0 | 14 | Denver | -1 | = | -1
Boise | Salt Lake City | 0 | 6
Butte | Seattle | 0 | 10
Butte | Boise | 0 | 7 | Total Distance: | 22
Butte | Salt Lake City | 0 | 7
Butte | Cheyenne | 0 | 12
Butte | Billings | 1 | 4 | Route: | Seattle->Butte->Billings->Cheyenne->Denver
Salt Lake City | Boise | 0 | 6
Salt Lake City | Butte | 0 | 7
Salt Lake City | Cheyenne | 0 | 7
Salt Lake City | Grand Junction | 0 | 5
Billings | Butte | 0 | 4
Billings | Cheyenne | 1 | 7
Cheyenne | Billings | 0 | 7
Cheyenne | Butte | 0 | 12
Cheyenne | Boise | 0 | 14
Cheyenne | Salt Lake City | 0 | 7
Cheyenne | Denver | 1 | 1
Grand Junction | Salt Lake City | 0 | 5
Grand Junction | Denver | 0 | 4
Denver | Cheyenne | 0 | 1
Denver | Grand Junction | 0 | 4